## Follow up list
List to Follow up | Date | owner | followup Status | comments
Access to Tilli Claude accounts for amit , Syed , Suryakanth | 2026-02-09 | Sushmitha | Done | sent the email
infra to work with hassan , to assign the github accounts for claude | 2026-02-09 | Sushmitha | Done | sent the email
once 1 , 2 is done , there is a docx folder in Git , Task list will be there , all the tasks will be given by Ali in the Task List ( updates can be found there ) | 2026-02-10 | Ali | Done | task list given out
Sushmitha to schedule a call - daily at 10 am EST | 2026-02-09 | Sushmitha | Done
Amit , Syed , Suryakanth to walk Ali through on what they have built till now for 5 mins each with AI. | 2026-02-10 | Sushmitha | Done | scheduled a demo , from the team
Draft Beacon AI development policy | 2026-02-11 | Dev Team | in progress | to merge as the single doc , et : 18-feb
Explore AI website builder within Beacon |  | Suryakant | inprogress | working on this
Follow up on Claude/GitHub access | 2026-02-10 | Sushmitha | Done | Access Provided
Review & harden existing Beacon components |  | Amit
Define sprint documentation & review process | 2026-02-17 | sushmitha | in progress
Claude Code Console Dev Access | 2026-02-13 | Infra | Done | followup call on 18-feb
Tilli / Google Partnership | 2026-02-11 | Sushmitha | Done | meeting invite sent to the team
work with Infra to get Dev built. | 2026-02-16 | Ali | Done
Allocate this one to the VSCode console for the team - Amit, Syed and Suryakant. | 2026-02-16 | Infra |  | worked for Amit , need to take confirmation from Surya and Syed
Tilli Beacon API Keys for AWS | 2026-02-16 | Ali | done | infra updated the requested autorization
AWS Dev ECS | 2026-02-16 | Infra |  | need to clarify with Ali | infra is working on it - to go with Node not the ubuntu version - Node Alpine
Mobile apllication access to Suryakanth | 2026-02-17 | sushmitha |  | sent out an email
TilliArc Endpoints for PDF | 2026-02-17 | Raja |  | followup email to raja sir
Follow-up Item | Context from Discussion | Action Required | Priority | Target
Create Detailed Project Plan | Ali asked for Sprint / Project plan | Convert task list into structured project plan | High | Immediate | inprogress
Create Jira Project & Tasks | Excel draft mentioned | Move task list into Jira with proper breakdown | High | This week
Get Estimates from Dev Team | Required before planning | Collect effort estimates (Syed, Amit, Surya, Hassan) | High | Before sprint finalization
Align Tasks with Ali’s Original Email | Ali asked to review original assignment list | Re-map tasks to correct owners (Beacon / Marketing / XDEX / Monay) | High | Immediate
Define MVP Scope Clearly (Beacon) | Multiple parallel discussions happening | Document MVP: ERP Sync, Financial Sync, Marketing Integration | High | Before next review
Track Access & Environment Issues | Devs had revoked access issue | Ensure infra stability & confirm access for all devs | Medium | Ongoing
Daily Tracker Circulation | Multiple complex modules discussed | Share structured daily tracker with status updates | High | Daily

## Claude task list
Beacon Dev Team — Task List
Last Updated: 2026-02-16 ¦ Branch: dev ¦ Developers: Syed (Dev 1), TBD (Dev 2), TBD (Dev 3)
Task ID | Task Description | Responsible Person | Category | Status | Priority | Notes | 2026-02-18
Developer 1 — XDEX Integration & Testing (Syed)
1.1 | Test and verify Google and Microsoft Auth works (passwordless, Google, Microsoft auth only) | Syed | Dev 1 – Syed | Pending | P0 | OAuth callback flow, JWT token issuance, session persistence
1.2 | Verify QuickBooks OAuth flow end-to-end (initiate auth, callback, token storage, refresh) | Syed | Dev 1 – Syed | Pending | P0 | Endpoint: POST /api/xdex/quickbooks/initiate-auth
1.3 | Verify QuickBooks customer sync maps correctly to contacts table | Syed | Dev 1 – Syed | Pending | P0 | Endpoint: POST /api/xdex/quickbooks/sync-customers
1.4 | Verify QuickBooks invoice sync maps correctly to erp_invoices table | Syed | Dev 1 – Syed | Pending | P0 | Endpoint: POST /api/xdex/quickbooks/sync-invoices
1.5 | Verify Oracle CC&B credential management and health check | Syed | Dev 1 – Syed | Pending | P1 | Endpoint: POST /api/xdex/oracle-ccb/set-credentials, test-connection
1.6 | Verify Oracle CC&B customer sync with deduplication guards (ccbAccountId, ccbPersonId) | Syed | Dev 1 – Syed | Pending | P1 | Endpoint: POST /api/xdex/oracle-ccb/sync-customers
1.7 | Test XDEX multi-tenant isolation — ensure tenant A cannot access tenant B data | Syed | Dev 1 – Syed | Pending | P0 | Per-tenant XDEX API keys in admin settings
1.8 | Test ERP Settings page (/settings/erp) — XDEX badge, credential UI, connection test buttons | Syed | Dev 1 – Syed | Pending | P1 | Frontend: apps/web/src/pages/ErpSettings.js
1.9 | Test onboarding Step 3 — ERP system selection with XDEX-ready badges | Syed | Dev 1 – Syed | Pending | P1 | Frontend: apps/web/src/pages/JareisOnboarding.tsx
1.1 | Write E2E Playwright test for XDEX QuickBooks sync flow | Syed | Dev 1 – Syed | Pending | P2 | Add to apps/web/e2e/
1.11 | Document XDEX sandbox limitations and update docs/XDEX_integration.md | Syed | Dev 1 – Syed | Pending | P2 | Sandbox: https://api.xdex-sbx.tilli.pro
Developer 2 — Nudge Integration & Messaging | [6 empty] | Hassan
2.1 | Test passwordless OTP login flow — Nudge SMS delivery, OTP verification, JWT issuance | TBD | Dev 2 – TBD | Pending | P0 | Route: apps/api/src/routes/auth.routes.ts
2.2 | Test passwordless OTP with email channel (not just SMS) | TBD | Dev 2 – TBD | Pending | P0 | Nudge client supports SMS + Email
2.3 | Verify Nudge webhook signature verification (SHA256) works in all environments | TBD | Dev 2 – TBD | Pending | P0 | File: apps/api/src/integrations/nudge/notifications.ts
2.4 | Test marketing campaign approval reminder emails via Nudge | TBD | Dev 2 – TBD | Pending | P1 | Service: notification-stats.service.ts
2.5 | Test billing notifications — payment reminders, overdue alerts | TBD | Dev 2 – TBD | Pending | P1 | Service: utility-nudges.service.ts
2.6 | Test workflow send_message step — SMS, email, WhatsApp channels | TBD | Dev 2 – TBD | Pending | P1 | Workflow engine step type
2.7 | Test notify_agent workflow step — agent notification delivery | TBD | Dev 2 – TBD | Pending | P1 | Workflow engine step type
2.8 | Verify Nudge delivery logs and analytics (nudge-logs.service.ts) | TBD | Dev 2 – TBD | Pending | P1 | Delivery/click tracking
2.9 | Test utility nudges — outage alerts, bill due reminders | TBD | Dev 2 – TBD | Pending | P2 | Service: utility-nudges.service.ts
2.1 | Verify Nudge v1 vs v2 send endpoint configuration works correctly | TBD | Dev 2 – TBD | Pending | P2 | Env: NUDGE_SEND_ENDPOINT=/v2/Nudge/Send
2.11 | Write E2E test for full OTP login → dashboard flow | TBD | Dev 2 – TBD | Pending | P2 | Extend passwordless-login.spec.ts; may need real Nudge integration
2.12 | Test omnichannel console — thread view, composer, template approvals | TBD | Dev 2 – TBD | Pending | P1 | Files: apps/web/src/components/omnichannel/
Developer 3 — End-to-End Testing & Quality | [6 empty] | Amit , Syed
3.1 | Run all existing E2E tests and fix any failures | TBD | Dev 3 – TBD | Pending | P0 | pnpm -C apps/web e2e (8 suites)
3.2 | Run all API smoke tests and fix any failures | TBD | Dev 3 – TBD | Pending | P0 | pnpm -C apps/api test:marketing, test:finance:tb-smoke
3.3 | Run finance smoke test — invoice, payment, bill, ledger posting via TigerBeetle | TBD | Dev 3 – TBD | Pending | P0 | pnpm -C apps/api test:finance:tb-smoke
3.4 | Run admin auth guardrails smoke test | TBD | Dev 3 – TBD | Pending | P0 | pnpm -C apps/api test:admin-auth
3.5 | Run workflow TODO actions smoke test (create_task, create_ticket, update_record, assign_agent, notify_agent, deflection) | TBD | Dev 3 – TBD | Pending | P0 | Tests: create_task, create_ticket, update_record, assign_agent, notify_agent, deflection
3.6 | Run CCB golden replay + schema drift tests | TBD | Dev 3 – TBD | Pending | P1 | pnpm -C apps/api test:ccb:golden, test:ccb:drift
3.7 | Set up Vitest for unit tests (API services layer) | TBD | Dev 3 – TBD | Pending | P1 | No unit test framework exists today
3.8 | Write unit tests for ledger.service.ts — TigerBeetle posting logic | TBD | Dev 3 – TBD | Pending | P1 | Critical financial logic
3.9 | Write unit tests for jareis-assistant.service.ts — rule-based suggestions | TBD | Dev 3 – TBD | Pending | P2 | Validate risk detection, sentiment, escalation logic
3.1 | Test TilliPay payment flow — card + ACH endpoints | TBD | Dev 3 – TBD | Pending | P1 | Routes: /api/tillipay/card, /api/tillipay/ach
3.11 | Test customer invoice lifecycle: create, add line items, send, record payment, void | TBD | Dev 3 – TBD | Pending | P1 | Routes: /api/customer-invoices/*
3.12 | Test vendor bill lifecycle: create, add line items, approve, pay, void | TBD | Dev 3 – TBD | Pending | P1 | Routes: /api/vendor-bills/*
3.13 | Test ledger reporting endpoints — balance sheet, income statement, journal entries | TBD | Dev 3 – TBD | Pending | P2 | Routes: /api/ledger/*
3.14 | Verify multi-tenant data isolation across all major entities | TBD | Dev 3 – TBD | Pending | P0 | Contacts, invoices, bills, tickets, workflows
3.15 | Apply finance migration to staging and run repair/audit scripts | TBD | Dev 3 – TBD | Pending | P0 | Migration: packages/db/drizzle/0003_curved_drax.sql
Cross-Team — Known Gaps (Assign as capacity allows)
X.1 | Complete GitHub OAuth server-side token exchange | TBD | Cross-Team | Pending | P2 | Auth route exists, GitHub API call incomplete
X.2 | Connect LLM (OpenAI/Anthropic) to Jareis ticket assistant | TBD | Cross-Team | Pending | P1 | Currently rule-based only; placeholder in jareis-assistant.service.ts
X.3 | Implement Contact Center call transfers (warm/cold) | TBD | Cross-Team | Pending | P2 | AWS Connect Streams integration
X.4 | Implement call recording playback UI | TBD | Cross-Team | Pending | P2 | S3 presigned URLs + audio player component
X.5 | Navigation redesign (collapsible sidebar, contextual tabs, mobile) | TBD | Cross-Team | Pending | P2 | Spec: docs/Beacon_Nav_2026.md
X.6 | Payment link generation via TilliPay | TBD | Cross-Team | Pending | P2 | Route skeleton exists, not wired

## Legend
Status / Priority Legend
PRIORITY
P0 | Must complete before staging / production
P1 | Required for launch readiness
P2 | Important but can follow initial launch
STATUS
Pending | Not started
In Progress | Actively being worked on
Done | Verified complete
SECTIONS
Dev 1 – Syed | XDEX Integration & Testing
Dev 2 – TBD | Nudge Integration & Messaging
Dev 3 – TBD | End-to-End Testing & Quality
Cross-Team | Known gaps — assign as capacity allows

## Task List - Ali
# | Task List | Status - feb 17 | Comments | Status - feb 18
1 | Infra to setup Docker for Postgress, Radis and Tiger beetle in Dev environment. No local installs please. >> Infra | in progress
2 | AI Policy and Procedure (merge the work of all product teams - Sushmita has the handle on documents from Beacon team) >> Raja owns this one. | inprogress
3 | Amit, Syed and Suryakant - VSCode Claude Console to git - no direct git access >> Work already cut out for them. >> Sushmitha to follow through | Amit : done , syed n surya kanth ro review
4 | Help on Monay (separate email on that soon) >> Ali to work with Infra tos et up Dev for Monay on Monay Pay AWS. Suryakant to work with Ali on MVP mobile launch. | to work with Suryakanth (pending) need to get the update
5 | Sriram and Abdul will join me and Hassan - nudge , Raja - Tilli arc | FYI
6 | tillipay (payin/payout) integration to Beacon >> Sriram | to work with Sriram
7 | Regression across all existing flows supported in Beacon >> Amit (Starting marketing hooks to all social media) | amit : in progress , to get the clarification from Ali | Amit to work on social media research - proposed the idea of Xdex integration
8 | XDEX integration to Beacon >> Abdul/Syed | Work on Api key with Xdex configration | to work with adbul - to sync 3 things [Customers , vendors , employees ],[invoices,bills ,payrolls , payments ] , to work with Sriram for the intergration for tilliPay
9 | Nudge Integration to Beacon >> Hassan
10 | tilliX (post login), integration to beacon >> Ibrahim
11 | tilliArc Integration to Beacon >> Raj (we load bills and have invoices - i am hoping oto use all documents / statements, etc. into TilliArc - right now direct to S3)
12 | Beacon Admin (Intrastate?) will be centralized to manage tilliX, Nudge, Beacon, tilliPay applications for internal purposes >> Ibrahim & Raja
13 | Target Integration Beacon Testing >> End of Feb (possible?)
14 | Production deployment Mid-March
15 | Beacon Product documentation >> Sravan/Hari,
16 | Pricing and subscription >> Sravan, Shabbir, Ali
17 | Update tillisoftware website >> Hari

## Feb 17
Beacon – Daily Status Update with MoM
Date: 17-Feb-2026
Project: Beacon
Meeting Type: Daily Sync
# | Task / Topic | Owner | Current Status | Discussion / Update (MoM) | Next Action | Priority | 2026-02-18 | 2026-02-19
1 | VS Code & Access Setup | Amit, Syed, Suryakant | done | Amit confirmed access working. Others yet to verify. | Syed & Surya to confirm setup replication | High | done
2 | XDEX Global API Config (Admin Level) | Syed | In Progress | API key configured at Super Admin. Tenant-level sync failing. | Debug API key usage & refactor config separation (Admin vs Tenant) | High | to look into this | working on onboarding import contacts - (bugs indentified while doing the code walkthrough
3 | QuickBooks via XDEX | Syed + Abdul | Issue Identified | Callback issue – appears direct QuickBooks auth instead of XDEX loop. | Abdul to verify callback path & authentication flow | High
4 | ERP Sync (Customers / Vendors / Employees) | Syed | In Progress | Need generic schema for multiple ERPs (Oracle, QuickBooks, FreshBooks, Xero). | Implement abstraction layer for ERP sync | High
5 | Financial Sync (Invoices, Bills, Payments, Payroll) | Syed | Pending | MVP requires: Sync Person + Sync Financials (Invoices & Bills minimum). | Prioritize connectivity → then invoice/bill push-back to ERP | High
6 | Marketing – Social Media Integration (LinkedIn, Google Ads) | Amit | Research Phase | LinkedIn & Google Ads partially integrated. Need unified admin-level integration. | Research best architecture (Aggregator vs Direct) | High | looking into previous imprementation for google | waiting for Linkedin keys ,
7 | Marketing Billing Logic | Amit | Not Started | Spend should flow to Enterprise Billing (Admin-controlled). | Design spend tracking + billing mapping | Medium
8 | Dynamic Multi-Step Form → Marketing Integration | Amit | Not Started | Forms created via Jarvis need to plug into Marketing campaigns. | MVP: Simple dynamic form → campaign linkage | Medium
9 | Social Media OAuth & Handle Mapping | Amit | Research Required | Users should only provide handle; platform authentication needed securely. | Research OAuth + key management model | High | to look into this
10 | TilliPay Integration | Syed + Sriram | Pending | TilliPay currently direct. Needs review for integration alignment. | Validate API keys + confirm working flow | Medium
11 | Onboarding Flow (ERP Connect During Signup) | Syed | Broken | ERP connection failing during onboarding flow. | Fix XDEX connection during signup stage | High
12 | Monay Walley(Mobile) | Suryakant + Ali | In Progress | Complex module. Separate 1:1 required. | Schedule detailed walkthrough | Medium | got the git access , started with the code review | got the repo access 2 days back , looking into login

## Tasks (old)
Task | Assignee | Assigned Date | 2026-02-12 | 2026-02-13 | 2026-02-17
1) http://localhost:4200/marketing end to end regression (marketing Campaign, onboarding using Dynamic Flow, ending into the Application for review of signed up /applicants - http://localhost:4200/applications, add hooks for all social media channels (R&D needed) | Assign to Amit | 2026-02-11 | working on the setup , connected with Hasaan . | working on marketing survey , to create the show Ali today | to discuss with Ali regarding the flow
2) Integration to XDEX http://localhost:4200/settings/erp - extend support for more then 1 ERPs with one key (e.g. Account Number, or complex - multiple keys mapping capability to be added - first name, last name, service zip code, or billing zip code, etc.), mapping across multiple backends. Use different tenants to test across QB, Oracle CC&B, SAP, etc. | Soheb to work with Abdul | 2026-02-11 | trying to run locally | ran the project locally, connected with adbul for xdex (working on structured approach) | no updates
3) Monay Mobile MVP - regression and thorough testing for end to end issues, and deploying the Monay stack to AWS CI. >> | Suryakant. | 2026-02-11 | to clarify with Ali. | local setup is done , need to get a brief walktrough on monay application | no updates