## Sheet1
# Beacon Dev Team — Task List
> **Last Updated:** 2026-02-16
> **Branch:** dev
> **Developers:** Dev 1 (Syed), Dev 2 (TBD), Dev 3 (TBD)
---
## Developer 1 — XDEX Integration & Testing (Syed)
XDEX integration code is ~95% complete (QuickBooks + Oracle CC&B). Focus is on **verification, edge cases, and E2E test coverage**.
¦ # ¦ Task ¦ Status ¦ Priority ¦ Notes ¦
¦---¦------¦--------¦----------¦-------¦
¦ 1.1 ¦ Test and verify Google and Microsoft Auth works. We only support passwordless, Google, and Microsoft auth. ¦ Pending ¦ P0 ¦ OAuth callback flow, JWT token issuance, session persistence ¦
¦ 1.2 ¦ Verify QuickBooks OAuth flow end-to-end (initiate auth, callback, token storage, refresh) ¦ Pending ¦ P0 ¦ Endpoint: `POST /api/xdex/quickbooks/initiate-auth` ¦
¦ 1.3 ¦ Verify QuickBooks customer sync maps correctly to `contacts` table ¦ Pending ¦ P0 ¦ Endpoint: `POST /api/xdex/quickbooks/sync-customers` ¦
¦ 1.4 ¦ Verify QuickBooks invoice sync maps correctly to `erp_invoices` table ¦ Pending ¦ P0 ¦ Endpoint: `POST /api/xdex/quickbooks/sync-invoices` ¦
¦ 1.5 ¦ Verify Oracle CC&B credential management and health check ¦ Pending ¦ P1 ¦ Endpoint: `POST /api/xdex/oracle-ccb/set-credentials`, `test-connection` ¦
¦ 1.6 ¦ Verify Oracle CC&B customer sync with deduplication guards (`ccbAccountId`, `ccbPersonId`) ¦ Pending ¦ P1 ¦ Endpoint: `POST /api/xdex/oracle-ccb/sync-customers` ¦
¦ 1.7 ¦ Test XDEX multi-tenant isolation — ensure tenant A cannot access tenant B data ¦ Pending ¦ P0 ¦ Per-tenant XDEX API keys in admin settings ¦
¦ 1.8 ¦ Test ERP Settings page (`/settings/erp`) — XDEX badge, credential UI, connection test buttons ¦ Pending ¦ P1 ¦ Frontend: `apps/web/src/pages/ErpSettings.js` ¦
¦ 1.9 ¦ Test onboarding Step 3 — ERP system selection with XDEX-ready badges ¦ Pending ¦ P1 ¦ Frontend: `apps/web/src/pages/JareisOnboarding.tsx` ¦
¦ 1.10 ¦ Write E2E Playwright test for XDEX QuickBooks sync flow ¦ Pending ¦ P2 ¦ Add to `apps/web/e2e/` ¦
¦ 1.11 ¦ Document any XDEX sandbox limitations and update `docs/XDEX_integration.md` ¦ Pending ¦ P2 ¦ Sandbox: `https://api.xdex-sbx.tilli.pro` ¦
**Key Files:**
- `apps/api/src/routes/xdex.routes.ts` (970 lines — all XDEX endpoints)
- `apps/web/src/pages/ErpSettings.js`
- `docs/XDEX_integration.md`
---
## Developer 2 — Nudge Integration & Messaging
Nudge messaging integration is complete but needs **testing across all channels and verification of webhook processing**.
¦ # ¦ Task ¦ Status ¦ Priority ¦ Notes ¦
¦---¦------¦--------¦----------¦-------¦
¦ 2.1 ¦ Test passwordless OTP login flow — Nudge SMS delivery, OTP verification, JWT issuance ¦ Pending ¦ P0 ¦ Route: `apps/api/src/routes/auth.routes.ts` ¦
¦ 2.2 ¦ Test passwordless OTP with email channel (not just SMS) ¦ Pending ¦ P0 ¦ Nudge client supports SMS + Email ¦
¦ 2.3 ¦ Verify Nudge webhook signature verification (SHA256) works in all environments ¦ Pending ¦ P0 ¦ File: `apps/api/src/integrations/nudge/notifications.ts` ¦
¦ 2.4 ¦ Test marketing campaign approval reminder emails via Nudge ¦ Pending ¦ P1 ¦ Service: `notification-stats.service.ts` ¦
¦ 2.5 ¦ Test billing notifications — payment reminders, overdue alerts ¦ Pending ¦ P1 ¦ Service: `utility-nudges.service.ts` ¦
¦ 2.6 ¦ Test workflow `send_message` step — SMS, email, WhatsApp channels ¦ Pending ¦ P1 ¦ Workflow engine step type ¦
¦ 2.7 ¦ Test `notify_agent` workflow step — agent notification delivery ¦ Pending ¦ P1 ¦ Workflow engine step type ¦
¦ 2.8 ¦ Verify Nudge delivery logs and analytics (`nudge-logs.service.ts`) ¦ Pending ¦ P1 ¦ Delivery/click tracking ¦
¦ 2.9 ¦ Test utility nudges — outage alerts, bill due reminders ¦ Pending ¦ P2 ¦ Service: `utility-nudges.service.ts` ¦
¦ 2.10 ¦ Verify Nudge `v1` vs `v2` send endpoint configuration works correctly ¦ Pending ¦ P2 ¦ Env: `NUDGE_SEND_ENDPOINT=/v2/Nudge/Send` ¦
¦ 2.11 ¦ Write E2E test for full OTP login → dashboard flow (extend `passwordless-login.spec.ts`) ¦ Pending ¦ P2 ¦ Existing test may need real Nudge integration ¦
¦ 2.12 ¦ Test omnichannel console — thread view, composer, template approvals ¦ Pending ¦ P1 ¦ Files: `apps/web/src/components/omnichannel/` ¦
**Key Files:**
- `apps/api/src/integrations/nudge/client.ts` (Nudge API client)
- `apps/api/src/integrations/nudge/notifications.ts` (webhook verification)
- `apps/api/src/services/nudge-logs.service.ts`
- `apps/api/src/services/utility-nudges.service.ts`
- `apps/api/src/services/notification-stats.service.ts`
**Environment:**
```
NUDGE_API_URL=https://app.nudge.net/api
NUDGE_SEND_API_URL=https://app.nudge.net/api
NUDGE_SEND_ENDPOINT=/v2/Nudge/Send
NUDGE_FROM_SMS=18448443464
NUDGE_FROM_EMAIL=notification@nudge.net
```
---
## Developer 3 — End-to-End Testing & Quality
Beacon has 8 E2E test suites + API smoke tests but **no unit tests and several coverage gaps**. This developer owns test infrastructure and overall quality.
¦ # ¦ Task ¦ Status ¦ Priority ¦ Notes ¦
¦---¦------¦--------¦----------¦-------¦
¦ 3.1 ¦ Run all existing E2E tests and fix any failures ¦ Pending ¦ P0 ¦ `pnpm -C apps/web e2e` (8 suites) ¦
¦ 3.2 ¦ Run all API smoke tests and fix any failures ¦ Pending ¦ P0 ¦ `pnpm -C apps/api test:marketing`, `test:finance:tb-smoke` ¦
¦ 3.3 ¦ Run finance smoke test — invoice, payment, bill, ledger posting via TigerBeetle ¦ Pending ¦ P0 ¦ `pnpm -C apps/api test:finance:tb-smoke` ¦
¦ 3.4 ¦ Run admin auth guardrails smoke test ¦ Pending ¦ P0 ¦ `pnpm -C apps/api test:admin-auth` ¦
¦ 3.5 ¦ Run workflow TODO actions smoke test ¦ Pending ¦ P0 ¦ Tests: create_task, create_ticket, update_record, assign_agent, notify_agent, deflection ¦
¦ 3.6 ¦ Run CCB golden replay + schema drift tests ¦ Pending ¦ P1 ¦ `pnpm -C apps/api test:ccb:golden`, `test:ccb:drift` ¦
¦ 3.7 ¦ Set up Vitest for unit tests (API services layer) ¦ Pending ¦ P1 ¦ No unit test framework exists today ¦
¦ 3.8 ¦ Write unit tests for `ledger.service.ts` — TigerBeetle posting logic ¦ Pending ¦ P1 ¦ Critical financial logic ¦
¦ 3.9 ¦ Write unit tests for `jareis-assistant.service.ts` — rule-based suggestions ¦ Pending ¦ P2 ¦ Validate risk detection, sentiment, escalation logic ¦
¦ 3.10 ¦ Test TilliPay payment flow — card + ACH endpoints ¦ Pending ¦ P1 ¦ Routes: `/api/tillipay/card`, `/api/tillipay/ach` ¦
¦ 3.11 ¦ Test customer invoice lifecycle: create, add line items, send, record payment, void ¦ Pending ¦ P1 ¦ Routes: `/api/customer-invoices/*` ¦
¦ 3.12 ¦ Test vendor bill lifecycle: create, add line items, approve, pay, void ¦ Pending ¦ P1 ¦ Routes: `/api/vendor-bills/*` ¦
¦ 3.13 ¦ Test ledger reporting endpoints — balance sheet, income statement, journal entries ¦ Pending ¦ P2 ¦ Routes: `/api/ledger/*` ¦
¦ 3.14 ¦ Verify multi-tenant data isolation across all major entities ¦ Pending ¦ P0 ¦ Contacts, invoices, bills, tickets, workflows ¦
¦ 3.15 ¦ Apply finance migration to staging and run repair/audit scripts ¦ Pending ¦ P0 ¦ Migration: `packages/db/drizzle/0003_curved_drax.sql` ¦
**Test Commands:**
```bash
pnpm test # All tests
pnpm -C apps/web e2e # Playwright E2E (8 suites)
pnpm -C apps/web e2e:real-smoke # Real browser smoke
pnpm -C apps/api test:marketing # Marketing approval tests
pnpm -C apps/api test:finance:tb-smoke # Finance/TigerBeetle smoke
pnpm -C apps/api test:approvals:api # Approval email tests
pnpm db:audit # Finance guardrails audit (if script exists)
```
**Key Files:**
- `apps/web/e2e/*.spec.ts` (8 E2E test suites)
- `apps/api/src/scripts/*-test.ts` (API smoke tests)
- `packages/db/src/audit-finance-guardrails.ts`
- `packages/db/src/repair-finance-guardrails.ts`
- `.github/workflows/` (3 CI pipelines)
---
## Cross-Team — Known Gaps (Assign as capacity allows)
¦ # ¦ Task ¦ Owner ¦ Status ¦ Priority ¦ Notes ¦
¦---¦------¦-------¦--------¦----------¦-------¦
¦ X.1 ¦ Complete GitHub OAuth server-side token exchange ¦ TBD ¦ Pending ¦ P2 ¦ Auth route exists, GitHub API call incomplete ¦
¦ X.2 ¦ Connect LLM (OpenAI/Anthropic) to Jareis ticket assistant ¦ TBD ¦ Pending ¦ P1 ¦ Currently rule-based only; placeholder in `jareis-assistant.service.ts` ¦
¦ X.3 ¦ Implement Contact Center call transfers (warm/cold) ¦ TBD ¦ Pending ¦ P2 ¦ AWS Connect Streams integration ¦
¦ X.4 ¦ Implement call recording playback UI ¦ TBD ¦ Pending ¦ P2 ¦ S3 presigned URLs + audio player component ¦
¦ X.5 ¦ Navigation redesign (collapsible sidebar, contextual tabs, mobile) ¦ TBD ¦ Pending ¦ P2 ¦ Spec: `docs/Beacon_Nav_2026.md` ¦
¦ X.6 ¦ Payment link generation via TilliPay ¦ TBD ¦ Pending ¦ P2 ¦ Route skeleton exists, not wired ¦
---
## Status Legend
- **P0** — Must complete before staging/production
- **P1** — Required for launch readiness
- **P2** — Important but can follow initial launch
- **Pending** — Not started
- **In Progress** — Actively being worked on
- **Done** — Verified complete

## Sheet2
# | Task List | Status | Comments
1 | Infra to setup Docker for Postgress, Radis and Tiger beetle in Dev environment. No local installs please. >> Infra | in progress
2 | AI Policy and Procedure (merge the work of all product teams - Sushmita has the handle on documents from Beacon team) >> Raja owns this one. | inprogress
3 | Amit, Syed and Suryakant - VSCode Claude Console to git - no direct git access >> Work already cut out for them. >> Sushmitha to follow through | Amit : done , syed n surya kanth ro review
4 | Help on Monay (separate email on that soon) >> Ali to work with Infra tos et up Dev for Monay on Monay Pay AWS. Suryakant to work with Ali on MVP mobile launch. | to work with Suryakanth (pending) need to get the update
5 | Sriram and Abdul will join me and Hassan - nudge , Raja - Tilli arc | FYI
6 | tillipay (payin/payout) integration to Beacon >> Sriram | to work with Sriram
7 | Regression across all existing flows supported in Beacon >> Amit (Starting marketing hooks to all social media) | amit : in progress ,
8 | XDEX integration to Beacon >> Abdul/Syed
9 | Nudge Integration to Beacon >> Hassan
10 | tilliX (post login), integration to beacon >> Ibrahim
11 | tilliArc Integration to Beacon >> Raj (we load bills and have invoices - i am hoping oto use all documents / statements, etc. into TilliArc - right now direct to S3)
12 | Beacon Admin (Intrastate?) will be centralized to manage tilliX, Nudge, Beacon, tilliPay applications for internal purposes >> Ibrahim & Raja
13 | Target Integration Beacon Testing >> End of Feb (possible?)
14 | Production deployment Mid-March
15 | Beacon Product documentation >> Sravan/Hari,
16 | Pricing and subscription >> Sravan, Shabbir, Ali
17 | Update tillisoftware website >> Hari