## FEB-11
1️⃣ Calendar Management
# | Task | Owner | Priority | Timeline | Status | Date | Follow up status
1 | Ensure Jyoti & Sushmitha have full access to Monay & Tilli calendars | Ali | High | Immediate | Pending | 2026-02-11 | Done
2 | Continue LinkedIn connects (Monay-specific / Tilli-specific messaging) | Jyoti | Medium | Ongoing | Done | 2026-02-11 | ongoing
3 | Clean calendar overlaps (move internal meetings only) | Jyoti | High | Ongoing | Done | 2026-02-11 | Done
4 | Do NOT move investor / external / C-level meetings | Jyoti | Critical | Ongoing | Done | 2026-02-11 | Done
5 | Reschedule family/personal invites to after-hours (5 PM+) | Jyoti | Medium | Ongoing | Done | 2026-02-11 | Proposed new time
2️⃣ Weekly Governance
# | Task | Owner | Priority | Timeline | Status
6 | Schedule recurring 30-min Monday sync (East Coast afternoon) | Sushmitha | High | Before next Monday | Done | 2026-02-11 | Done
7 | Use weekly sync for planning & alignment | Ali + Team | High | Weekly | Done | 2026-02-11 | Done
3️⃣ Compliance / Legal Documentation
# | Task | Owner | Priority | Timeline | Status
8 | Obtain Delaware Statement of Good Standing | Jyoti | Critical | Immediate | Done | 2026-02-11 | Done
9 | Use Amex if payment required | Jyoti | High | Immediate | Done | 2026-02-11 | Done
10 | Coordinate with Finance (Sanjay / Suresh / Srinivas) | Jyoti | High | Immediate | Done | 2026-02-11 | Done
11 | Share entity details with Julio | Jyoti | High | Immediate | Done | 2026-02-11 | Done
12 | Confirm Julio received all required documents | Jyoti | High | Immediate | Done | 2026-02-11 | Done
4️⃣ Developer Execution (Beacon / Monay)
# | Task | Owner | Priority | Timeline | Status
13 | Review AI Policy draft (Amit, Suryakant, Syed) | Ali | High | Tomorrow | Done | 2026-02-11 | Sent the email
14 | First major dev task (setup, access, GitHub) | Dev Team | High | ~1 week | Done | 2026-02-11 | pending
15 | Implement Buds–Roses–Thorns framework | Ali | High | Immediate | Done | 2026-02-11 | done
16 | Daily → 2-day → Weekly cadence transition | Ali | Medium | Progressive | Done | 2026-02-11
17 | Clarify TLX vs Beacon workload balance | Sushmitha | High | Next Sync | Done | 2026-02-11 | done
5️⃣ Access & Infrastructure
# | Task | Owner | Priority | Timeline | Status
18 | Approve Monay proposal before granting repo access | Ali | High | TBD | Pending | 2026-02-11
19 | Coordinate with Infra to assign GitHub access (Suryakant) -Monay | Ali + Infra | High | Post-approval | Done | 2026-02-11 | Done
6️⃣ Insurance / External Meeting
# | Task | Owner | Priority | Timeline | Status
20 | Confirm Insurance meeting (Tuesday, 3 PM EST) | Jyoti | High | Immediate | Done | 2026-02-11 | Done
21 | Verify Sriram’s availability | Jyoti | High | Immediate | Done | 2026-02-11 | Done

## FEB-17
Task | Owner | Details | Deadline | Status | Comments
Fund Bank Account | Jyoti / Ali | Fund newly opened account with $250 minimum balance | By 21st | Pending | Done
Confirm with Julio | Jyoti | Respond to Julio’s email after funding confirmation | After funding | Pending
AWS Dev – ECS Setup | Infra | Set up Amazon Elastic Container Service (ECS) environment | ASAP | In Progress | Done
Node Base Image Configuration | Infra | Use Node Alpine (slim version) as Docker base image (not Ubuntu) | Along with ECS setup | Pending | Done
Clarify Node Version | Sushmitha | Confirm correct Node Alpine version with Ibrahim / ABM model if needed | ASAP | Pending | done
DDR Endpoints Review | Dev Team | Review and confirm DDR endpoints configuration | ASAP | Pending | Done

## FEB -23
# | Topic | Action Item | Owner | Timeline | Status
1 | Outlook Calendar Access | Sync and confirm shared calendar visibility | Jyoti | Immediate | Done
2 | M&T Bank Deposit Requirement | Inform Raj to deposit $27.78 (10%) before first two transactions | Jyoti | Before first 2 transactions | Done
3 | Bank Documents | Send voided check copy | Ali | Completed (sent via email) | Done
4 | DocuSign – Transfer Capabilities | Follow up with M&T for signed confirmation copy | Ali | ASAP | Done
5 | Insurance Policy Renewal (ENO) | Respond with approximate customer exposure numbers (minimal disclosure) | Jyoti | Immediate | Done
6 | Property Purchase | Negotiate price (target ~$400K range); continue exploring alternatives | Ali / Jyoti | Ongoing
7 | Microsoft/Meta/Ads Accounts | Use existing Telepro accounts; coordinate with Infra team | Sushmitha / Hari | Immediate | Done
8 | Generic Microsoft Account Setup | Infra team to configure using existing Azure/Telepro setup | Infra Team | ASAP | Done
9 | Monipay Repo Permissions | Adjust branch permissions (remove full write; follow Beacon model) | Infra Team | High Priority | Done
10 | Tilli Endpoint Document | Resend Tilli endpoint document to Ali (Teams/email) | Raja | Immediate | Done
11 | Travel Schedule | Cancel meetings on 25th & 26th; set out-of-office | Ali / Jyoti | Before travel | Done
12 | Task Documentation | Document meeting outcomes and track follow-ups in Teams | Sushmitha | Daily follow-up | on goinng